## Instructions
Instructions for Completing the Sample 2050 Comprehensive Plan Work Plan
Use this template to outline your community’s approach to completing the 2050 Comprehensive Plan update. Keep entries concise and tailored to your local context.
The content of this Sample Work Plan and Budget is an example template. You may modify this template to document your communities specific timeline and milestones.
Adjust scope and level of detail based on your community’s size, capacity, and complexity.
Ensure timelines are realistic and account for review, revisions, and approvals.
You will be able to update your Work Plan at the mid-point check-in. This should just be based on the best information available at the time.
General Information
Fill in the city name and date at the top.
Estimate the total project duration (in months) based on your anticipated schedule.
If you intend to claim the Early Plan Completion Incentive, please note that your plan must be deemed complete no later than October 31 2028, and you must submit your plan to the Met Council no later than October 10 2028. (Latest date to allow Council staff 15 business days to review for completeness. We recommend submitting it earlier than this as very few submissions are deemed complete upon their first review.)
Provide realistic start and end timeframes based on your best information at the time.
Identify how each portion of the project will be managed (staff, consultants, or both).
Section 1: Project Administration and Community Involvement
This section should consider how the project will be managed (staff, consultants, or both).
This may include defining the structure and role of a steering committee, if any, including number of meetings (if known).
Section 2: Community Engagement, Workgroups, Public Meetings
Outline your public engagement approach, adjusting activities (meetings, workshops, outreach methods) to fit your community.
Section 3: Community Character, Profile, and Future Vision
Include tasks and timelines that summarize the data and analysis you will complete (population, housing, employment, etc.).
This would include identifying your growth forecasts and community designation(s) and how they will inform planning.
This could include any additional trend analysis relevant to your local conditions (demographics and community profile).
Section 4: Required Plan Elements
For each of the sections below, include tasks and timelines that briefly summarize how you will analyze each topic to plan for future development, including mapping, density, and alignment with regional policy.
Land Use
Housing
Transportation
Water Resources
Wastewater
Surface Water
Water Supply
Regional Parks and Trails
Climate
Natural Systems
Implementation Plan
Describe how the plan will be carried out, including policies, programs, and investments.
Include development of a Capital Improvements Program (CIP) and any needed updates to local controls (e.g., zoning).
Section 5. Distribution to adjacent/affected jurisdictions
Consider tasks and timelines that accommodate the required six-month distribution to others for review of the comp plan.
Section 6. Plan Submittal to Met Council for review
Identify the timeline necessary for Met Council review, taking into consideration whether you wish to receive funds for early plan completion.
Section 7: Advancing People-Centered Regional Goals
Identify which regional goal(s) your plan will advance and list corresponding strategies.
Section 8: Early Plan Completion
For Early Plan Completion, include tasks and timelines that ensure plan submission no later than October 10, 2028.
It is recommended that you allow for additional time to account for review, revisions, and approvals, both locally and from the Met Council.
Budget Instruction
Estimated Cost (Grant-funded)
List costs expected to be included as part of the work. Use best estimates- this information can change overtime.
The Met Council will utilize this information to understand how the Planning Assistance Grants contribute to the local comprehensive plan process and total project cost. This will help inform future planning assistance grant program budgets.

## Work Plan and Budget TEMPLATE
City/County/Twp of ______________________ 2050 Comprehensive Plan Update
Proposed Work Plan - TEMPLATE, FOR ILLUSTRATIVE PURPOSES ONLY |  |  |  | Expected
Date: ______________________ |  |  |  | Budget
| Estimated Start Date | Estimated Completion | Task Lead (Staff/Consultant) | Estimated Cost
TOTAL - COMPREHENSIVE PLAN UPDATE | Date | Date |  | 0
SECTION A: BASE WORKPLAN
1: Project Administration and Community Involvement |  |  |  | $-
2: Community Engagement, Workgroups, Public Meetings |  |  |  | $-
3: Community Character, Profile and Future Vision |  |  |  | $-
4: Required Plan Elements |  |  |  | $-
Land Use |  |  |  | $-
Housing |  |  |  | $-
Transportation |  |  |  | $-
Water Resources |  |  |  | $-
Wastewater
Surface Water
Water Supply
Parks and Trails |  |  |  | $-
Climate |  |  |  | $-
Natural Systems |  |  |  | $-
Implementation Plan |  |  |  | $-
5. Distribution to adjacent/affected jurisdictions
Preliminary Plan review to the Met Council
6. Plan Submittal to Met Council for review
SECTION B: Advancing Regional Goals
7: Advancing People-Centered Regional Goals
Our regional is equitable and inclusive |  |  |  | $-
Our communities are healthy and safe |  |  |  | $-
Our region is dynamic and resilient |  |  |  | $-
SECTION C: Early Submission Incentive
8: Early Plan Completion (by October 31, 2028) |  |  |  | $-
If you intend to claim the Early Plan Completion Incentive, please note that your plan must be deemed complete no later than October 31 2028, and you must submit your plan to the Met Council no later than October 10 2028.

## Work Plan and Budget SAMPLE
City/County/Twp of ______________________ 2050 Comprehensive Plan Update
Proposed Work Plan - SAMPLE, FOR ILLUSTRATIVE PURPOSES ONLY |  |  |  | Expected
Date: ______________________ |  |  |  | Budget
| Estimated Start Date | Estimated Completion | Task Lead (Staff/Consultant) | Estimated Cost
TOTAL - COMPREHENSIVE PLAN UPDATE | Date | Date |  | 0
SECTION A: BASE WORKPLAN
1: Project Administration and Community Involvement | 2026-05-01 | 2026-06-30 |  | $-
Consultant Selection & Project Administration
Organization and Staffing of Steering Committee
Develop & manage project website and facebook page
2: Community Engagement, Workgroups, Public Meetings | 2026-06-01 | 2028-09-01 |  | $-
Develop and distribute project publicity materials
Host two (2) Community Visioning Sessions
Host two (2) Land Use, Transportation, and Design Workshops
Conduct one (1) public open house
Conduct one (1) public hearing
3: Community Character, Profile and Future Vision | 2026-06-01 | 2026-12-31 |  | $-
Identification and Analysis of Population, Household, Employment, and other community characteristics
Identification of IMAGINE Community Designation(s) and Related Policy
Assessment of regional and national demographic, economic, and environmental trends, issues, and opportunities
4: Required Plan Elements | 2027-01-01 | 2028-01-01 |  | $-
Land Use |  |  |  | $-
Map existing land use
Analyze forecasts for population, households, and employment
Map and calculate future land use and land supply
Develop land use policies (density, mixed use, resource protection)
Housing |  |  |  | $-
Compile data on existing housing stock and affordability
Analyze housing needs across income levels
Identify housing gaps and priority needs
Develop housing policies, tools, and implementation strategies
Transportation |  |  |  | $-
Map and analyze roadway system and functional classification
Assess traffic volumes, safety trends, and priority corridors
Map transit routes, facilities, freight. bike and ped networks, and service areas
Develop multimodal strategies and safety improvements
Water Resources |  |  |  | $-
Wastewater |  |  |  | $-
Map existing sewer infrastructure and service areas
Analyze system capacity and forecasted demand
Identify inflow and infiltration (I/I) issues
Plan for future sewer service and expansions
Surface Water |  |  |  | $-
Inventory lakes, rivers, wetlands, and watershed areas
Assess impacts of land use on water resources
Coordinate with watershed organizations and plans
Develop protection, management, and restoration strategies
Water Supply |  |  |  | $-
Analyze existing water demand and future needs
Identify water sources, capacity, conservation strategies and limitations
Assess system infrastructure and vulnerabilities
Plan for future improvements and system expansion
Parks and Trails |  |  |  | $-
Map existing parks, trails, and facilities
Assess access, gaps, and connectivity. Plan for expansion.
Identify regional and local system coordination needs
Develop policies and capital improvement priorities
Climate |  |  |  | $-
Assess greenhouse gas emissions and climate risks
Identify vulnerable populations and infrastructure
Evaluate impacts of land use and transportation
Develop mitigation and adaptation strategies
Natural Systems |  |  |  | $-
Map natural resources (wetlands, habitats, tree canopy, etc.)
Assess condition and ecological function
Identify areas for protection and restoration
Develop conservation and management policies
Implementation Plan |  |  |  | $-
Identify priority actions and strategies
Develop timelines and phasing
Align with Capital Improvements Program (CIP)
Update local controls (e.g., zoning, ordinances)
5. Distribution to adjacent/affected jurisdictions | 2028-03-01 | 2028-09-01 |  | $-
Preliminary Plan review to the Met Council | 2028-03-01 | +/-90 days
6. Plan Submittal to Met Council for review | 2028-10-10 | 2028-10-31 |  | $-
SECTION B: Advancing Regional Goals
7: Advancing People-Centered Regional Goals
Our regional is equitable and inclusive
Our communities are healthy and safe
Our region is dynamic and resilient
SECTION C: Early Submission Incentive
8: Early Plan Completion (by October 31, 2028) | 2028-10-10 | 2028-10-31
If you intend to claim the Early Plan Completion Incentive, please note that your plan must be deemed complete no later than October 31 2028, and you must submit your plan to the Met Council no later than October 10 2028.
DISCLAIMER: The examples in this sample work plan are for illustrative purposes only. Communities should customize their work plans to reflect their specific conditions, priorities, and project approach.