## Invest & Cleanup Estimate
TBRA - SAMPLE INVESTIGATION & CLEAN-UP BUDGET | [5 empty] | Public Sources |  |  |  | Private Sources |  | Total - Sum of Sources
A | SITE INVESTIGATION AND RESPONSE ACTION PLANNING |  |  |  | Project Cost | TBRA | DEED | County ERF | Other (Public) | Private | Comment
| Phase I |  |  |  | 5000 | 0 | 0 | 0 | 0 | 5000 | Completed 9 months ago | 0
| Phase I Update |  |  |  | 2000 | 1500 |  |  |  | 500 |  | 0
| Phase II |  |  |  | 40000 | 35000 | 0 | 0 | 0 | 5000 |  | 0
| Preparation of RAP |  |  |  | 8000 | 5000 | 0 | 0 | 0 | 3000 |  | 0
| Asbestos and Lead-based Paint Survey |  |  |  | 6000 | 4000 | 0 | 0 | 0 | 2000 |  | 0
A | Subtotal Site Investigation and RAP |  |  |  | 61000 | 45500 | 0 | 0 | 0 | 15500
| % Investigation Match (Minimum 25%) | [8 empty] | 25.41%
B1 | RESPONSE ACTION PLAN IMPLEMENTATION - CLEANUP COSTS
| Contaminated Soil Management | Quantity | Unit | Rate
| Mobilization | 1 | LS | 5000 | 5000 | 1000 | 2000 | 0 | 0 | 2000 |  | 0
| Excavation of contaminated soils | 4000 | CY | 5 | 20000 | 3000 | 15000 | 2000 | 0 | 0 |  | 0
| Transportation of contaminated soils | 4000 | CY | 13 | 52000 | 7000 | 35000 | 10000 | 0 | 0 |  | 0
| Disposal of contaminated soils | 6000 | TONS | 18 | 108000 | 10500 | 80000 | 10000 | 0 | 7500 |  | 0
| Hazardous waste soil management | 300 | TONS | 50 | 15000 | 2000 | 12000 | 1000 | 0 | 0 |  | 0
| Back-fill | 4000 | CY | 5 | 20000 | 1000 | 8000 | 1000 | 0 | 10000 |  | 0
| Demobilization | 1 | LS | 5000 | 5000 | 1000 | 2000 | 0 | 0 | 2000 |  | 0
0
B2 | Field Work - Soils
| Soil Monitoring, Testing and Management Oversight (5 days @ $1,000 per day) | 5 | DAYS | 1000 | 5000 | 1000 | 2000 | 1000 | 0 | 1000 |  | 0
| Laboratory Analysis (DRO, VOC’s PAHs, RCRA Metals) (10 sets at $250 per set) | 10 | SET | 250 | 2500 | 500 | 1500 | 250 | 0 | 250 |  | 0
0
B3 | Soil Vapor Mitigation System
| Trench and rock fill |  |  |  | 30000 | 0 | 15000 | 0 | 0 | 15000 |  | 0
| Vapor Barrier 10,000 SF @ $1,50 per SF | 5000 | SF | 1.5 | 7500 | 2500 | 4000 | 1000 | 0 | 0 |  | 0
| System Blower Electrical & Installation |  |  |  | 5000 | 0 | 3000 | 0 | 0 | 2000 |  | 0
| System Design and Engineering |  |  |  | 6000 | 0 | 5000 | 0 | 0 | 1000 |  | 0
| Vapor System Installation Oversight | 2 | DAYS | 1000 | 2000 | 0 | 1500 | 0 | 0 | 500 |  | 0
| Post Construction Vapor Testing | 10 | SET | 1000 | 10000 | 2000 | 7000 | 0 | 0 | 1000 |  | 0
B4 | Other Cleanup Costs
| Remove underground petroleum storage tank | 1 | LS | 3500 | 3500 | 3500 | 0 | 0 | 0 | 0 | Not eligible for DEED funds | 0
| Installing and Removing Temporary Monitoring Wells |  |  |  | 2000 | 1000 | 0 | 0 | 0 | 1000 |  | 0
| Asbestos Abatement |  |  |  | 77800 | 70000 | 0 | 0 | 0 | 7800 | Not eligible for DEED funds | 0
| Lead-Based Paint (LBP) Abatement |  |  |  | 34500 | 30000 | 0 | 0 | 0 | 4500 | Not eligible for DEED funds | 0
B5 | Other Project Costs
| Implementation Report |  |  |  | 5500 | 1000 | 3500 | 1000 | 0 | 1000 |  | -1000
| MPCA Voluntary Program Evaluation |  |  |  | 3000 | 750 | 1500 | 500 | 0 | 250 |  | 0
| Subtotal Cleanup Implementation |  |  |  | 419300 | 137750 | 198000 | 27750 | 0 | 56800 |  | -1000
| TOTAL INVESTIGATION & CLEANUP |  |  |  | 480300 | 183250 | 198000 | 27750 | 0 | 72300 |  | -1000
| % Share |  |  |  |  | 38.15% | 41.22% | 5.778% | 0% | 15.05%
Note on K46: If applying to DEED, eligible private match -- as determined by DEED -- must be 12% or more.

## Asbestos Summary & Estimate
TBRA - SAMPLE UNIT COSTS FOR ASBESTOS ABATEMENT
| Location | Suspect Material Description | Friable (F)/Non-Friable (NF) | Unit Quantity | Unit | Unit Costs | Extension Cost
Basement
|  | 1 inch to 6-inch fibrous pipe insulation | F | 220 | LF | 20 | 4400
|  | 7- inch to 12-inch aircell pipe insulation | NF | 80 | LF | 22 | 1760
|  | 6-inch pipe fittings | NF | 9 | Each | 45 | 405
|  | 12-inch pipe fittings | NF | 3 | Each | 45 | 135
|  | Boiler door & gasket | F | 2 | Each | 25 | 50
|  | Boiler drum | F | 32 | SF | 35 | 1120
|  | Electrical panel | NF | 1 | Each | 100 | 100
1st Floor
|  | 12x12 inch floor tile and mastic | NF | 4200 | SF | 3 | 12600
|  | Wall Joint Compound | NF | 200 | SF | 2 | 400
|  | Tan Window Caulk | NF | 1500 | LF | 4 | 6000
|  | Sink undercoating | NF | 2 | Each | 65 | 130
|  | Fire Doors | NF | 2 | Each | 200 | 400
2nd Floor
|  | 9x9 inch floor tile | NF | 1600 | SF | 3 | 4800
|  | 12x12 inch ceiling tile & adhesive | F | 1200 | SF | 8 | 9600
3rd Floor
|  | Plaster | F | 1200 | SF | 2 | 2400
|  | Floor tile mastic | NF | 6000 | SF | 2 | 12000
|  | Grey vinyl baseboard | NF | 300 | LF | 1.5 | 450
|  | 2 X 4 foot ceiling panels & adhesive | NF | 300 | SF | 4 | 1200
Roof
|  | Grey Caulking on Roof | NF | 500 | LF | 9 | 4500
|  | Black Flashing | NF | 500 | LF | 5 | 2500
| Abatement Mobilization/Demobilization of Containment Area | [5 empty] | 625
| Abatement Design Manual and Specifications |  |  | 25 | Hours | 125 | 3125
| Abatement Project Oversight & Air Monitoring |  |  | 30 | Hours | 95 | 2850
| Asbestos Closeout Report |  |  | 50 | Hours | 125 | 6250
| TOTAL - ASBESTOS ABATEMENT | [5 empty] | 77800

## Lead-Based Paint Summary & Est.
TBRA - SAMPLE UNIT COSTS FOR LEAD-BASED PAINT ABATEMENT
Surface Area
| Location | Abatement Method | Walls | Columns | Walls (Stairwell) | Rails (Stairwell) | Other | Subtotal LBP- Quantity | Unit | Rate | Extension Cost
Basement
| Grey Paint | Stabilize & encapsulate | 800 | 400 | 75 |  |  | 1275 | SF | 2 | 2550
| Beige Paint | Stabilize & encapsulate |  |  |  | 62 |  | 62 | LF | 2.25 | 139.5
1st Floor
| Grey Paint | Removal | 800 | 400 | 75 |  |  | 1275 | SF | 4 | 5100
| Beige Paint | Removal |  |  |  | 60 |  | 60 | LF | 2.25 | 135
| Windows | Removal |  |  |  |  | 8 | 8 | Each | 90 | 720
2nd Floor
| Grey Paint | Removal | 800 | 400 | 75 |  |  | 1275 | SF | 4 | 5100
| Beige Paint | Removal |  |  |  | 60 |  | 60 | LF | 2.25 | 135
| Windows | Removal |  |  |  |  | 12 | 12 | Each | 90 | 1080
3rd Floor
| Grey Paint | Removal | 800 | 400 | 75 |  |  | 1275 | SF | 4 | 5100
| Beige Paint | Removal |  |  |  | 60 |  | 60 | LF | 2.25 | 135
| Windows | Removal |  |  |  |  | 12 | 12 | Each | 90 | 1080
West (Exterior Advertising)
| Flaking Sign Paint | Stabilize & encapsulate | 300 |  |  |  |  | 300 | SF | 16 | 4800
| Abatement Mobilization/Demobilization of Containment Area | [6 empty] | 1 | LS | 625 | 625
| Abatement Design Manual and Specifications | [6 empty] | 20 | Hours | 125 | 2500
| Abatement Project Oversight & Air Monitoring | [6 empty] | 40 | Hours | 95 | 3800
| Closeout Report | [6 empty] | 12 | Hours | 125 | 1500
| TOTAL - LEAD-BASED PAINT ABATEMENT | [9 empty] | 34499.5